## Sheet1
Gamperaliya Programe 2018
Physical and Financial Progress of the Month of | [6 empty] | 2019-01-31 15:16
Divisional Secretariate Division - Name
Divisional Secretariate Division - No |  |  |  | 1212 | [12 empty] | 104-2-6-20-2506
අනු අංකය | ව්‍යාපෘතිය | වසම | වසම් අංකය | සංරචකය | ව්‍යාපෘතියේ ස්භාවය | ඇස්තමේන්තුව |  | වෙන්කළ මුදල රු | වියදම (රු) | මිණුම් ඒකක |  | භෞතික ප්‍රගතිය | [9 empty] | ප්‍රතිලාභීන් සංඛ්‍යාව | වෙනත් කරුණු
[6 empty] | වැට් සහිතව | වැට් රහිතව |  |  | ඒකකය | ප්‍රමාණය | A | B |  |  |  | C | D | E | F | G
[13 empty] | B1 | B2 | B3 | B4
1 | ඉදිගොල්ලාගම ශ්‍රී අභිනවාරාම විහාරස්ථානයේ ධර්ම ශාලාව සකස් කිරීම | දකුණු සියඹලන්ගමුව | 463 | SW | CO |  | 984182.44 | 990000 | 970000 | [11 empty] | 1 | 220
2 | පහල ඕබඩයාගම ශ්‍රී ශෛලබිම්බාරාම විහාරස්ථානයේ ඉදිවෙමින් පවතින මකර තොරණේ වැඩ නිම කිරීම | ඕබඩයාගම | 486 | SW | CO |  | 485000 | 495000 | 485000 | [11 empty] | 1 | 475
3 | ශ්‍රී මුනින්දාරාම විහාරස්ථානයේ සංඝාවාස ගොඩනැගිල්ල ප්‍රතිසංස්කරණය කර ගැනීම | හදුන්ගම | 476 | SW | CO |  | 485000 | 495000 | 485000 | [11 empty] | 1 | 360
4 | මදේල්ලෑව ගල්පොකුණ විහාරස්ථානය ප්‍රතිසංස්කරණය කිරීම | මිදෙල්ලෑව | 483 | SW | CO |  | 485000 | 495000 | 485000 | [11 empty] | 1 | 575
5 | ගල්නෑව නෑගම මොහිදීන් ජුම්මා පල්ලිය වැසිකි පද්ධතිය සකස් කිරීම | නෑගම | 462 | SW | CO |  | 399700.12 | 396000 | 388000 | [11 empty] | 1 | 410
[8 empty] | 2871000 | 2813000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2040 | 0
Rural Water Supply
Rural Electricity
Improvement of Rural Access
Community Development
Minor Irrigation (Construction and Reconstruction of Canals, Anicuts, Pounds, Wells, under the Minor irrigation Projects for Agricultural Activities)
Social Welfare
Social Service
Community Protection
Rural Economy
Other
Estimates are being prepared
For Construction - B1 Estimates Prepared & Bid Documents approved, B2 = Qutation /Bid Called, B3=Qutation Received, B4= Contract Awared
For Construction , Start Construction works, 40% Completed, Other : Placed Order for Goods
For Construction : 60% Completed , Other : Received Goods / instruments as per the Order
For construction 80% Completed,Other Received Goods /intsruments as per the Order
For construction 99% Completed,Other Completed lists of Goods and Beneficiaries
For construction 100% Completed,issued Goods and Insruments to Identified institutions /CBOs