## Sheet1
Rural Infrastructure Development Specail Programe (Stage 11) - 2018
Physical and Financial Progress of the Month of | [6 empty] | 2019-01-31 15:18
Divisional Secretariate Division - Name
Divisional Secretariate Division - No |  |  |  | 1212 | [13 empty] | 104-2-6-6-2506
Sn | Name Of The Project |  |  | Sector | Type of Project (Construction/ Good & Services) | Total Estimate Cost (Rs) |  | Allocation Rs. | Expenditure (Rs) | Measurements |  | Physical Prograss © | [9 empty] | Num. of Benificiaries | Remarks
[6 empty] | With VAT | Without VAT |  |  | Units | Quantity | A | B |  |  |  | C | D | E | F | G
[13 empty] | B1 | B2 | B3 | B4
1 | මැදවච්චිය අසල වැව පාර මීටර් 500 ක් බොරළු දමා සකස් කිරීම | මැදවච්චිය | 466 | RA | CO |  | 497500 | 497500 | 170002.98 | [9 empty] | 1 |  |  | 1200
2 | කෝරළේ මහතාගේ නිවස අසල සිට මීටර් 500 ක් බොරළු දමා සකස් කිරීම | කරුවලගස්වැව | 481 | RA | CO |  | 497500 | 497500 | 494931.7 | [11 empty] | 1 | 85
3 | ගල්නෑව පන්සල මාර්ගය තාර යොදා ප්‍රතිසංස්කරණය කිරීම | ගල්නෑව ගම | 472 | RA | CO |  |  | 995000 | 860850.81 | [11 empty] | 1 | 600
4 | ගල්නෑව තොන්නකෝන් මහතාගේ නිවස ඉදිරිපිට මාර්ගය කුට්ටිගල් අතුරා සංවර්ධනය කිරීම | ගල්නෑව නගරය | 477 | RA | CO |  | 981944.8 | 995000 | 989094.8 | [11 empty] | 1 | 800
5 | අවුකන දුම්රිය පොළ ආසන්නයේ උද්‍යානය හා උද්‍යානයයේ යාබද මාර්ගය සංවර්ධනය කිරීම | වලස්වැව | 474 | CD | CO |  |  | 995000 | 85395.34 | [8 empty] | 1 |  |  |  | 600
6 | කටුකුඹුර හන්දියේ සිට කල්ලංචිය හන්දිය දක්වා මාර්ගය සංවර්ධනය කිරීම | කල්ලංචිය | 465 | RA | CO |  |  | 995000 | 979254.68 | [11 empty] | 1 | 750
7 | ගල්නෑව ප්‍රාදේශීය ලේකම් කොට්ඨාසයේ යෞවන සමාජ සඳහා කාය වර්ධන උපකරණ ලබා දීම | ප්‍රා.ලේ. කොට්ඨාශය | 15 | CD | PU |  | 0 | 995000 | 990000 | [11 empty] | 1 | 1500
[7 empty] | 1976944.8 | 5970000 | 4569530.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 5 | 5535
Rural Water Supply
Rural Electricity
Improvement of Rural Access
Community Development
Minor Irrigation (Construction and Reconstruction of Canals, Anicuts, Pounds, Wells, under the Minor irrigation Projects for Agricultural Activities)
Social Welfare
Social Service
Community Protection
Rural Economy
Other
Estimates are being prepared
For Construction - B1 Estimates Prepared & Bid Documents approved, B2 = Qutation /Bid Called, B3=Qutation Received, B4= Contract Awared
For Construction , Start Construction works, 40% Completed, Other : Placed Order for Goods
For Construction : 60% Completed , Other : Received Goods / instruments as per the Order
For construction 80% Completed,Other Received Goods /intsruments as per the Order
For construction 99% Completed,Other Completed lists of Goods and Beneficiaries
For construction 100% Completed,issued Goods and Insruments to Identified institutions /CBOs